AI CUSTOMER SUPPORT CHATBOT

Project Documentation

BRD  |  FRD  |  UAT Report  |  Change Request & Impact Analysis

| Field | Details |
| --- | --- |
| Client | ShopSmart Solutions Pvt. Ltd. |
| Industry | E-Commerce / Retail / IT |
| Project Name | AI-Powered Customer Support Chatbot |
| Document Version | v2.1 |
| Prepared By | Business Analyst |
| Date | April 2025 |
| Status | In Progress — CR Under Review |

# SECTION 1: BUSINESS REQUIREMENTS DOCUMENT (BRD)

## 1.1 Executive Summary

ShopSmart Solutions Pvt. Ltd. is a fast-growing e-commerce and retail company operating across web and mobile platforms. The organization was experiencing a high volume of repetitive customer support queries — including order tracking, product inquiries, return requests, and account-related issues — that were consuming significant human agent time and increasing operational costs.

This project proposes the development and deployment of an AI-powered Customer Support Chatbot to automate Tier-1 customer interactions, reduce resolution time, and enhance the overall customer experience through 24/7 availability.

## 1.2 Business Objectives

- Automate 70% of Tier-1 customer support queries through AI-driven chatbot interaction.

- Reduce average customer query resolution time from 8 minutes to under 2 minutes.

- Decrease customer support operational cost by 40% within 12 months of deployment.

- Improve Customer Satisfaction Score (CSAT) from 67% to 85% within two quarters.

- Provide 24/7 support availability across web and mobile platforms without additional staffing.

## 1.3 Problem Statement

ShopSmart's support team was handling over 4,500 customer queries per day. Approximately 72% of these queries were repetitive in nature — order status, return eligibility, product availability, and account password resets. Human agents were spending an average of 8 minutes per ticket, resulting in long wait times, poor customer satisfaction, and high employee burnout. There was no automated system in place to triage or resolve common queries.

## 1.4 Scope

In Scope:

- AI Chatbot deployment on the ShopSmart website and mobile app.

- Natural Language Processing (NLP) based query understanding and response generation.

- Integration with Order Management System (OMS), CRM, and product catalog.

- Escalation to human agent for complex queries.

- Multilingual support for English and Hindi.

- Admin dashboard for chatbot performance monitoring.

Out of Scope:

- Voice-based customer support integration (planned for Phase 2).

- Social media chatbot deployment (planned for Phase 3).

- Backend OMS or CRM development — integration only.

## 1.5 Stakeholders

| Stakeholder | Role | Responsibility |
| --- | --- | --- |
| Mr. Rajesh Mehta | Client Sponsor | Final approval on scope and budget |
| Ms. Priya Sharma | Product Owner | Requirements sign-off and prioritization |
| Business Analyst | BA / PM | Documentation, coordination, client communication |
| Dev Team Lead | Technical Lead | Architecture, development oversight |
| QA Lead | Quality Assurance | UAT planning and execution |
| Customer Support Head | End User Rep | Feedback and UAT participation |

## 1.6 Assumptions & Constraints

Assumptions:

- Client will provide API access to OMS and CRM systems within Week 2 of project kickoff.

- The chatbot will handle text-based interactions only in Phase 1.

- Client's IT team will manage server infrastructure and hosting.

Constraints:

- Project must go live within 16 weeks from kickoff.

- Chatbot must comply with DPDP Act 2023 (India) data privacy regulations.

## 1.7 Business Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Delayed API access from client | Medium | High | Escalate to sponsor in Week 1 |
| Low chatbot accuracy on edge cases | High | Medium | Train on historical data; human fallback |
| User resistance to chatbot | Low | Medium | UX testing; smooth escalation flow |
| Data privacy compliance failure | Low | High | Legal review before go-live |

# SECTION 2: PROJECT WORKFLOW & TIMELINE

## 2.1 Project Timeline Overview

The project is planned across 16 weeks from kickoff to go-live. Each phase has clearly defined deliverables, owners, and exit criteria.

| Phase | Weeks | Activities | Deliverables |
| --- | --- | --- | --- |
| Phase 1 Project Kickoff & Discovery | Week 1 – Week 2 | Project kickoff meeting, stakeholder alignment, API access collection, environment setup, requirement elicitation sessions with client team. | Signed project charter, stakeholder register, API access confirmed, kickoff meeting minutes. |
| Phase 2 Requirements & Documentation | Week 3 – Week 4 | Detailed requirement gathering, business process mapping, BRD preparation, client review and sign-off on requirements. | Approved BRD v1.0, use case list, scope confirmation document. |
| Phase 3 Functional Design | Week 5 – Week 6 | Prepare FRD, define functional requirements (FR-01 to FR-06), data flow diagrams, UI/UX wireframes, NLP intent mapping. | Approved FRD v1.0, wireframes, intent library, API contract document. |
| Phase 4 Development — Core Chatbot | Week 7 – Week 10 | AI chatbot development — NLP engine setup, OMS integration, CRM integration, returns module, escalation engine, admin dashboard. | Working chatbot on staging environment, API integration complete, internal build sign-off. |
| Phase 5 Internal QA & Testing | Week 11 – Week 12 | Functional testing, regression testing, performance testing (response time, concurrent users), security testing, bug fixes. | QA test report, defect log, performance benchmark results, security review sign-off. |
| Phase 6 User Acceptance Testing (UAT) | Week 13 – Week 14 | Client team executes UAT on staging environment, BA coordinates testing sessions, defects logged and tracked, client feedback incorporated. | UAT report, defect resolution log, UAT sign-off from client. |
| Phase 7 Change Request Review | Week 14 – Week 15 | CR-2025-007 (Personalization & Memory Engine) submitted by client, impact analysis prepared, pros/cons reviewed, recommendation shared with client. | CR Impact Analysis Document, recommendation report, client decision. |
| Phase 8 Go-Live & Handover | Week 16 | Production deployment, go-live monitoring, final documentation handover, training session for client admin team, project closure. | Live chatbot on production, final project report, training material, closure sign-off. |

## 2.2 Milestone Summary

| Milestone | Target Week | Status |
| --- | --- | --- |
| Project Kickoff & API Access | Week 1 | Completed |
| BRD Approved by Client | Week 4 | Completed |
| FRD Approved by Client | Week 6 | Completed |
| Development Complete (Staging) | Week 10 | Completed |
| QA Sign-off | Week 12 | Completed |
| UAT Phase 1 Complete | Week 14 | Completed — 85.7% Pass Rate |
| CR-2025-007 Impact Analysis Submitted | Week 15 | In Progress |
| Production Go-Live | Week 16 | Upcoming |

# SECTION 3: FUNCTIONAL REQUIREMENTS DOCUMENT (FRD)

## 3.1 System Overview

The AI Customer Support Chatbot is a web and mobile-integrated intelligent assistant built on a large language model (LLM) backbone with a rule-based fallback engine. It communicates with the ShopSmart backend via REST APIs and provides real-time responses to customer queries.

## 3.2 Functional Requirements

FR-01: User Authentication Recognition

| Attribute | Detail |
| --- | --- |
| Requirement ID | FR-01 |
| Module | User Authentication |
| Description | The chatbot shall identify logged-in users via session token and greet them by name. |
| Priority | High |
| Acceptance Criteria | Chatbot displays user first name within 1 second of chat initiation. |

FR-02: Natural Language Query Processing

| Attribute | Detail |
| --- | --- |
| Requirement ID | FR-02 |
| Module | NLP Engine |
| Description | The chatbot shall understand natural language queries and map them to defined intents. |
| Priority | Critical |
| Acceptance Criteria | Intent recognition accuracy >= 88% on test dataset of 500 sample queries. |

FR-03: Order Status Enquiry

| Attribute | Detail |
| --- | --- |
| Requirement ID | FR-03 |
| Module | OMS Integration |
| Description | The chatbot shall fetch and display real-time order status when a customer provides an order ID or is authenticated. |
| Priority | Critical |
| Acceptance Criteria | Order status retrieved and displayed within 3 seconds with 99.5% uptime. |

FR-04: Return & Refund Request Handling

| Attribute | Detail |
| --- | --- |
| Requirement ID | FR-04 |
| Module | Returns Management |
| Description | The chatbot shall allow customers to initiate return requests and check refund eligibility based on policy rules. |
| Priority | High |
| Acceptance Criteria | Return request initiated successfully; customer receives confirmation message with ticket ID. |

FR-05: Human Agent Escalation

| Attribute | Detail |
| --- | --- |
| Requirement ID | FR-05 |
| Module | Escalation Engine |
| Description | The chatbot shall detect unresolved or complex queries and offer seamless handoff to a live agent. |
| Priority | High |
| Acceptance Criteria | Escalation triggered within 2 failed resolution attempts; full chat history passed to agent. |

FR-06: Admin Monitoring Dashboard

| Attribute | Detail |
| --- | --- |
| Requirement ID | FR-06 |
| Module | Admin Panel |
| Description | Admins shall have access to a real-time dashboard showing chat volumes, resolution rates, escalation rates, and CSAT scores. |
| Priority | Medium |
| Acceptance Criteria | Dashboard loads in < 5 seconds; data refreshes every 60 seconds. |

## 3.3 Non-Functional Requirements

| NFR ID | Category | Requirement |
| --- | --- | --- |
| NFR-01 | Performance | Chatbot response time must be under 2 seconds for 95% of queries. |
| NFR-02 | Availability | System uptime must be >= 99.5% monthly. |
| NFR-03 | Security | All user data encrypted at rest and in transit (AES-256, TLS 1.3). |
| NFR-04 | Scalability | System must handle 2,000 concurrent users without degradation. |
| NFR-05 | Compliance | Must comply with DPDP Act 2023 data retention and privacy policies. |

## 3.4 Use Cases

| Use Case | Actor | Description |
| --- | --- | --- |
| UC-01: Start Chat | Customer | Customer initiates chat session on website or app. |
| UC-02: Query Resolution | Customer + AI | AI processes query and returns accurate response. |
| UC-03: Order Tracking | Customer + OMS | Customer asks for order status; system fetches from OMS. |
| UC-04: Raise Return Request | Customer + System | Customer submits return; system validates and logs. |
| UC-05: Escalate to Agent | Customer + Agent | AI detects unresolved issue and transfers to human agent. |
| UC-06: Monitor Performance | Admin | Admin views chatbot analytics via dashboard. |

## 3.5 Data Flow Summary

- Customer sends a message via chat widget on website or app.

- Message is passed to the NLP engine for intent classification.

- Based on intent, the system queries the relevant API (OMS, CRM, Product Catalog).

- Response is formatted and returned to the customer within the chat interface.

- Interaction is logged in the CRM for reporting and quality review.

- If escalation is triggered, full chat transcript is passed to the human agent console.

# SECTION 4: UAT TESTING REPORT

## 4.1 UAT Overview

| Field | Detail |
| --- | --- |
| Testing Phase | User Acceptance Testing (UAT) — Phase 1 |
| Testing Period | March 10, 2025 – March 21, 2025 |
| Environment | Staging Server (https://staging.shopsmart.in/chatbot) |
| Conducted By | QA Lead + Client Team + Business Analyst |
| Total Test Cases | 42 |
| Passed | 36 |
| Failed | 4 |
| Deferred | 2 |
| Overall Pass Rate | 85.7% |

## 4.2 Test Execution Summary

| TC ID | Module | Test Description | Status | Remarks |
| --- | --- | --- | --- | --- |
| TC-001 | Authentication | Logged-in user greeted by name on chat open | Pass | Verified |
| TC-002 | NLP Engine | Query 'where is my order' correctly mapped to order tracking intent | Pass | Verified |
| TC-003 | OMS Integration | Order status fetched correctly for valid Order ID | Pass | Verified |
| TC-004 | OMS Integration | Error message displayed for invalid Order ID | Pass | Verified |
| TC-005 | Returns Module | Return request raised for eligible order | Pass | Verified |
| TC-006 | Returns Module | Return blocked for order outside 7-day return window | Pass | Verified |
| TC-007 | Escalation | Escalation triggered after 2 failed resolution attempts | Pass | Verified |
| TC-008 | Escalation | Chat history correctly transferred to live agent | Pass | Verified |
| TC-009 | NLP Engine | Accuracy test on 50 mixed queries — achieved 86% | Pass | Meets threshold |
| TC-010 | Performance | Response time under 2 seconds for 95% of queries | Pass | Avg: 1.4s |
| TC-011 | Admin Dashboard | Dashboard loads within 5 seconds | Fail | Bug: 7.2s load time |
| TC-012 | Multilingual | Hindi language queries correctly processed | Fail | 3 intents misclassified |
| TC-013 | Security | Session token not exposed in chat logs | Pass | Verified |
| TC-014 | Returns Module | Refund amount displayed correctly | Fail | Rounding error on GST |
| TC-015 | NLP Engine | Handles offensive language gracefully | Pass | Redirects to agent |
| TC-016 | Admin Dashboard | CSAT score updates in real-time | Fail | 30-min delay observed |
| TC-017 | Scalability | 500 concurrent users without degradation | Deferred | Load test env pending |
| TC-018 | Compliance | Data deletion request handled within 72 hours | Deferred | Policy process ongoing |

## 4.3 Defect Summary

| Defect ID | Severity | Module | Description | Status |
| --- | --- | --- | --- | --- |
| DEF-001 | Medium | Admin Dashboard | Dashboard load time exceeds 5s SLA — observed 7.2s | Open — Fix In Progress |
| DEF-002 | High | Multilingual NLP | Hindi intent misclassification on 3 query types | Open — NLP Retraining Required |
| DEF-003 | Medium | Returns Module | GST rounding error in refund amount display | Open — Fix Scheduled |
| DEF-004 | Low | Admin Dashboard | CSAT score showing 30-min delay instead of real-time | Open — Config Issue |

## 4.4 UAT Sign-off Status

UAT Phase 1 is complete with an 85.7% pass rate. The 4 open defects are being tracked and resolved by the development team. Deferred test cases will be re-executed in UAT Phase 2 scheduled for April 7–11, 2025. Client has provided conditional approval to proceed.

| Sign-off | Name | Role | Status | Date |
| --- | --- | --- | --- | --- |
| Client Approval | Ms. Priya Sharma | Product Owner | Conditional Approval | March 22, 2025 |
| QA Approval | QA Lead | Quality Assurance | Approved with Defects Logged | March 22, 2025 |
| BA Acknowledgment | Business Analyst | Business Analyst | Acknowledged | March 22, 2025 |

# SECTION 5: CHANGE REQUEST — AI PERSONALIZATION & MEMORY ENGINE

## 5.1 Change Request Details

| Field | Detail |
| --- | --- |
| CR Number | CR-2025-007 |
| Requested By | Ms. Priya Sharma (Product Owner — ShopSmart) |
| Date Raised | March 25, 2025 |
| Priority | High |
| Status | Under Review |
| Reference Document | CR-2025-007 New Requirements Document (Separate) |

## 5.2 Change Request Description

The client has requested a new feature — an AI Personalization and Memory Engine. The feature will enable the chatbot to remember individual user interactions, including questions asked, products browsed, purchases made, and issues raised in previous sessions.

When a returning user opens the chatbot, the AI agent will greet them personally, reference their previous activity, and proactively offer relevant assistance — creating a highly personalized and context-aware support experience.

Example Scenario:

A customer named Arjun had previously purchased a blue running shoe and had asked about its return policy. When Arjun visits the website again 10 days later and opens the chat, the AI greets him: 'Welcome back, Arjun! I see you recently purchased Blue Bolt Running Shoes. Would you like help with your order, or do you have any questions today?' This significantly improves user experience and retention.

Note: Full functional requirements (FR-07 to FR-10) for this change request are documented in the separate CR-2025-007 New Requirements Document.

# SECTION 6: PROS & CONS OF NEW FEATURE

## 6.1 Advantages

| # | Benefit | Business Impact |
| --- | --- | --- |
| 1 | Enhanced Customer Experience | Personalized greetings and contextual responses improve customer satisfaction and loyalty. |
| 2 | Faster Query Resolution | Pre-loaded user context eliminates repetitive Q&A, reducing resolution time by ~30%. |
| 3 | Higher Conversion Rate | Proactive suggestions based on past purchases can drive 15–20% uplift in return visits. |
| 4 | Reduced Agent Load | Contextual AI handles more cases, reducing escalations to human agents by ~20%. |
| 5 | Competitive Differentiation | Personalized AI chatbots used by <5% of Indian e-commerce platforms — strong differentiator. |
| 6 | Behavioral Data | Interaction history provides rich data for marketing and product strategy decisions. |

## 6.2 Risks & Disadvantages

| # | Risk | Severity | Notes |
| --- | --- | --- | --- |
| 1 | Data Privacy Risk | High | Storing interaction history increases breach exposure. Requires DPDP Act compliance and strict encryption. |
| 2 | Increased Development Complexity | High | Memory engine needs new infrastructure — session store, history DB, retrieval logic. |
| 3 | Potential User Discomfort | Medium | Some users may find personalized greetings intrusive. Opt-out is mandatory. |
| 4 | Performance Overhead | Medium | Fetching user history adds latency. Needs optimization to stay within 2s response SLA. |
| 5 | Storage Cost Increase | Medium | Storing 90-day history for all users at scale increases infrastructure costs. |
| 6 | Model Hallucination Risk | Low | AI may incorrectly reference past interaction. Requires strict retrieval accuracy testing. |

# SECTION 7: IMPACT ANALYSIS

## 7.1 Timeline Impact

The AI Personalization & Memory Engine is a significant scope addition. The current plan targets go-live at Week 16. The new feature requires approximately 4–5 additional weeks of development, testing, and integration.

| Phase | Original Timeline | Revised Timeline | Additional Time |
| --- | --- | --- | --- |
| Development | Week 5 – Week 10 | Week 5 – Week 13 | +3 Weeks |
| QA & Integration Testing | Week 11 – Week 13 | Week 14 – Week 16 | +2 Weeks |
| UAT Phase 2 | Week 14 – Week 15 | Week 17 – Week 18 | +2 Weeks |
| Go-Live | Week 16 | Week 20 | +4 Weeks Total |

Recommendation:

Option A — Include Memory Engine in Phase 1 and accept the 4-week go-live delay. Option B — Launch chatbot on original timeline and deliver Memory Engine as Phase 2 within 6 weeks post go-live. The BA recommends Option B to protect the original go-live and allow sufficient time for proper compliance and testing of the new feature.

## 7.2 Technical Impact

| Component | Impact | Action Required |
| --- | --- | --- |
| Database | New user_interaction_history table + indexing required in PostgreSQL | DB schema redesign and migration planning |
| API Layer | New endpoints for history retrieval, consent management, and data deletion | API documentation and versioning update |
| NLP / AI Engine | Prompt engineering to incorporate user history context into LLM responses | Model prompt redesign and regression testing |
| Security | New PII data must be encrypted and access-controlled | Security review and penetration testing |
| Frontend | Consent banner and opt-out toggle to be added to chat interface | UI/UX design and frontend development |

## 7.3 Resource Impact

| Resource | Current Allocation | Additional Requirement |
| --- | --- | --- |
| Backend Developer | 1 developer full-time | +1 developer for 5 weeks |
| AI/ML Engineer | Shared (50%) | Full-time for 3 weeks (NLP prompt redesign) |
| QA Engineer | 1 engineer | No change — extended timeline covers it |
| Legal / Compliance | Not allocated | 1 external legal review session required |
| Business Analyst | Full-time | Additional documentation and client communication |

## 7.4 Risk Summary

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Go-live delay affects seasonal campaign | High | High | Recommend Option B to protect original launch date |
| Budget overrun if scope creeps further | Medium | High | Freeze scope after CR approval; strict change control |
| Data breach from history storage | Low | Critical | Encrypt all PII, DPDP compliance audit before launch |
| NLP accuracy drops with context injection | Medium | High | Run A/B testing on personalized vs standard responses |

# SECTION 8: DOCUMENT REVISION HISTORY

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| v1.0 | Feb 10, 2025 | Business Analyst | Initial BRD draft submitted for client review. |
| v1.1 | Feb 18, 2025 | Business Analyst | Stakeholder table updated; scope revised per client feedback. |
| v1.5 | Mar 01, 2025 | Business Analyst | FRD added with 6 functional requirements and NFR table. |
| v2.0 | Mar 22, 2025 | Business Analyst | UAT Phase 1 report and defect log added. |
| v2.1 | Mar 28, 2025 | Business Analyst | CR-2025-007 Impact Analysis and Recommendations added. |

— End of Document —